## Sheet1
Task | Hours Estimated | Complete? | Hours Spent | Total Expected Time | Total Time Spent | % Completed | % Budget Used | Multiplier
Complete Functional Diagram | 1 | complete | 1.5 | 35 | 1.5 | 2.9 | 4.3 | 1.48
Complete Gyro Handler | 1
Complete Button Handler | 1
Complete Physics Engine | 12
Complete Gameplay Logic | 10
Complete Render Logic | 8
Complete Functional Tests | 2